## Template for institutions
HREiR Action plan template (2023-2025)
Details
| Institution name: | Institute of Cancer Research |  |  |  | The institutional audience* for this action plan includes (only include direct beneficiaries; complete or delete, as appropriate):
| Cohort number: | 2 |  |  |  | Audience (direct beneficiaries of the action plan) |  | Number of | Comments
| Date of submission: | 2026-01-31 |  |  |  | Research staff |  | 316 | Made up of postdocs and equivalent grades (210), faculty/clinical faculty and senior staff scientists and CDF (106)
| Institutional context: | The ICR is a Research Institute of ~1200 staff. Audience for the Researcher Development Concordat was identified in 2020 by Research Leadership Board as those on the academic career track whose primary role was conducting research i.e. postdoc and equivalent level grades (including research fellows, staff scientists, and analytical scientist grades 3 and 4). |  |  |  | Postgraduate researchers |  | 150 | All PhD or MDRes
[6 empty] | Research and teaching staff |  | 0
[6 empty] | Teaching-only staff |  | 0
[6 empty] | Technicians |  | 410 | Of whom ~50% are trials/statistics and software roles - captured within Technician Commitment
[6 empty] | Clinicians |  | 36 | not already counted within the "research staff" section
[6 empty] | Professional support staff |  | 370 | of whom 54 are within scientific divisions (EAs, ops managers etc)
Other (please provide numbers and details):
Complete for submission | [7 empty] | To be completed only when reporting on action plan
| Obligation | Action | Carried over from previous action plan? | Deadline | Responsibility | The targeted impact of the action (success measure) | Comments (optional) | Progress update | The actual impact of the action (reporting against the success measure) | Outcome (ongoing/carried forward/no further action)
Environment and Culture
Awareness and engagement
The aims of these obligations are to work towards an open and inclusive research culture, and to ensure broad understanding and awareness of this amongst researchers.
ECI1 | Ensure all relevant staff are aware of the Concordat. | a) Share highlights of annual Researcher Concordat reports to the Research Leadership Board with all staff b)include a specific section of the monthly training newsletter for Research Culture (Concordat & Technician commitment) to communicate key info of interest in a way that is relevant to researchers. | yes | 2023-09-01 | RDM | Aim for 70% Concordat awareness in 2023 researcher training survey |  | Met - Awareness of Researcher Concordat measured in the annual training survey. Our KPI was to increase awareness from 50 to 70% by 2024,(2024 result 73%). Concordat information is now embedded in i) induction materials and ii) appraisal window launch. Training uptake data is shared annually at the postdoc conference and to ICR leadership as part of the Annual Concordat Report to Executive Board and Board of Trustees | Five years ago the Concordat working group asked for a section to be added to the ICR's appraisal form for researchers and their managers to review and plan minimum of 10 days professional development as part of the appraisal conversation. Survey data shows that the majority of postdoc and equivalent grades are taking their 10 days per year with very few queries about the process coming to the training team (as had been the case when first introduced). This 10 days of professional development model formed the basis for the ICR-wide CPD policy, drafted in 2025 and awaiting final approval, which will extend this expectation of protected development time for all staff | No further action
ECI2 | Ensure institutional policies and practices relevant to researchers are inclusive, equitable and transparent, and are well-communicated to researchers and their managers. | As a result of the pandemic and to support researchers to deal with the impact of this - the Equality Manager will be supporting the ICR to review a number of existing policies incuding: academic promotions policy, tenure review policy, workforce agreement, maternity, flexible working & B&H. | yes | 2024-09-01 | EDIM/Deputy Director HR | Equality manager and/HR colleagues to come to Staff Association meetings once every 12 months to share policy updates with the group & highlight how researchers can get involved in shaping these |  | Met - The introduction of a new ERP was agreed in 2024, as a result all core HR policies and processes were reviewed, updated and approved by Management Committee (includes researcher leaders on its membership). In addition to improving the people processes themselves, moving to the ERP improves the standardisation which which they can be applied and transparency of process for researchers and their managers | The new ERP makes it easier for researchers to search policies and understand their application (AI search function) as well as to update line managers of updates. The policies have been updated with input from researchers eg. Athena SWAN working group for parental leave policy updates and approved with Staff Side. | No further action
ECI6 | Regularly review and report on the quality of the research environment and culture, including seeking feedback from researchers, and using the outcomes to improve institutional practices. | Report and Support tool to be launched ICR-wide by Dec 2022. The portal seeks to address focus group feedback (following 2021 survey) around the need for anonymised reporting & will aid with hotspot reporting for the B&H task group. Uptake of tool reported to senior boards after first 6-12 months. | yes | 2023-12-01 | Deputy directors HR | Aim for 75% satisfaction with support for wellbeing and mental health support and 70% feeling effective tackling of B&H in the next all staff survey planned for spring 2023 |  | Not met - 2023 survey results showed that 69% of postdocs and 71% of group leaders agreed that the ICR provides good guidance and support for mental health and wellbeing which falls a little short of the 75% KPI. A 'morale' survey was requested by leadership in spring 2025 to explore this topic in greater detail. 70% of postdocs and 68% of research leaders said they felt able to sustain their current pace of work over the long term without it affecting their wellbeing | In response to survey data, Management Committee have set up the Wellbeing Working Group as a single forum to monitor wellbeing in the work place and report its findings to the ICR's senior management via regular reports to the ICR's Health Safety and Environment Committee. The group's first action is to review the newly agreed ICR Wellbeing Strategy and consider priorities for delivery in year one. | Ongoing -ACTION 1 forward action plan
ECR1 | Encourage researchers to actively contribute to the development and maintenance of a supportive, fair and inclusive research culture and be a supportive colleague, particularly to newer researchers and students. | Embedded into BAU | [5 empty] | Postdoc Assocaition and Student Committee co-developed a mentoring scheme in 2024 where postdocs mentor a students outside their own division. Evaluation at 6 and 12 months were positive and the initiative will be repeated annually. There were more mentors than mentees, showing strong postdoc support for initiatives enhancing research culture and wellbeing. In 2024/25 the Research Degree Supervisor Training was refreshed, putting a focus on peer to peer learning, with case studies to explore researcher wellbeing and the role of the supervisor. All supervisors will now need to participate in refresher training every 4 (rather than every 5 years previously) | Six postdoc-student pairs were matched, we followed up with the mentors so that any who were not contacted in the first couple of months of the scheme could re-enter the mentor pool. Pairs were matched on the basis of what they had said they would like support in and could offer support in respectively. Pairs met between 1 and 3 times over the 12 months. Those who responded to evaluation requests said having a mentor was a positive addition to their PhD experience and they would recommend it to others. The new supervisor training gathered also received strong positive feedback, with participants commenting that they valued the opportunity to share challenges and experiences with peers, and that having the procected time to do this was very valuable | No further action
Wellbeing and mental health
The aims of these obligations are to champion positive wellbeing amongst researchers, both through appropriate training and enabling new ways of working.
ECI3 | Promote good mental health and wellbeing through the effective management of workloads and people. | Academic Services holds a list of existing Faculty responsiblities (champion roles, committees - including external funding panels). Where new roles are required e.g. Faculty Champion for Researcher Concordat this list is key to inviting people to new roles. In addition the ICR are introducing a Managing Workplace Stress policy supported by a toolkit which includes: workplace risk assessment and action plan, stress self-assessment tool, printable guidance on how to have a conversation about workplace stress and online (on demand) stress awareness training. | yes | 2023-12-01 | Deputy directors HR | Aim for 75% satisfaction with support for wellbeing and mental health support and 70% feeling effective tackling of B&H in the next all staff survey planned for spring 2023. Additional question for 2023 to establish the proportion experiencing B&H within last 12 months with the option to select whether due to workload pressure to aid with hotspot reporting |  | Not met - A new question was included in the 2023 survey (following the Wellcome report into research culture) to explore the proportion of staff experiencing bullying and harassment. Highest scores were amongst research leaders citing the cause as "workload pressure" or "unreasonable demands". As a result, ICR launched a Report and Support platform, with staff encouraged to report incidents anoymously if they wish. The Employee Assistance programme was also enhanced (e.g. providing 250 hours of e-learning content, 8 couselling sessions if clinically appropriate and access to a digital gym) | ICR-wide survey scores were shared with all staff. The CEO personally promoting the introduction of the Report and Support tool to all staff, emphasising a zero tolerance approach to unacceptable behaviour. The link to Report and Support is pinned to the intranet homepage so that all researchers can access and report incidents. There are clear comms on the platform that the Wellbeing manager is responsible for tracking the number of reports logged on the portal as well as the numbers accessing the Employee Assistance Programme and online wellbeing portal, but that no other staff have access. Opportunities and events provides by the EAP are communicated in the weekly internal newsletter | Ongoing -ACTION 2 forward action plan
ECI4 | Ensure managers of researchers are effectively trained in relation to wellbeing and mental health. | Effective wellbeing and mental health training offered as part of 3 mandatory training courses (general induction, a supportive workplace and Health and Safety for line managers) and all managers must complete stress awarenss training within their first 6 months probation. In addition HR advisors personally invite those managers in need of upskilling in this area to Mental Health Awareness Training (run by Mental Health first aid). Monitor the extent to which managers feel effectively trained via Staff Attitude Survey. | yes | 2024-01-01 | Wellbeing & occ. heath coordinator & Deputy director HR | In 2021 61% of ICR research leaders/managers felt they were given good training to do their current job - aim to increase this to 75% with the introduction of wellbeing and mental health topics in manager's toolkits. Get 3 current managers to input on and pilot a training plan for new managers to refresh these topics and be able to monitor this |  | Met - In the 2023 survey 73% of research leaders felt they were given good training. Whilst the KPI was 75%, this is a good improvement on the 2021 figure of 61%. This figure was higher for postdocs at 83%. Mandatory Supervisor training was refreshed and mandated for all research degree supervisors in 2024. Wellbeing and mental health was one of the core themes included in the refresher - now delivered to ~75 research leaders with additional catch up sessions scheduled for 2025/26 academic year | Impact of the survey data includes stress awareness training introduced as a mandatory module for all staff (including managers) at the ICR and a for all research degree supervisors to refresh their training in the 2024/5 academic year. Feedback on the Supervisor training has been resoundingly positive with several group leaders commenting that it was the most helpful course they had attended in their time at ICR | Ongoing -ACTION 1 forward action plan
ECM3 | Ensure managers promote a healthy working environment that supports researchers' wellbeing and mental health. | In addition to introduction of Report and Support in Dec 2022, 2023 will see the launch of the ICR's Wellbeing action plan which commits line managers to role modelling wellbeing practices. | yes | 2023-09-01 | Wellbeing & occ. health coordinator/Deputy director HR | Monitor local survey scores by division/directorate for 2023 staff attitude survey for the question "I feel pressured to work additional hours regularly" and aim for <10% agree. Send managers the new policy and reminders of responsibilities in this area where not meeting the target |  | Met - Scores for this question were monitored in the 2023 - there were small variations between research divisions but the average across all was 9% agreeing. | Management Committee have requested that from 2026 engagement surveys will enable reporting at the team level, enabling managers to have more oversight and ownership of their team's research culture. In response to researcher feedback, future questions will clearly distinuish been answering about 'own team' or 'wider organisation' and reduce variablity in how current questions are interpretted. | Ongoing -ACTION 3 forward action plan
ECM4 | Ensure managers consider fully flexible working requests and other appropriate arrangements to support researchers. | Embedded into BAU | [7 empty] | No further action
ECR3 | Ensure researchers take positive action towards maintaining their wellbeing and mental health. | Continue to advertising opportunities to become a wellbeing advisor through the staff associations to ensure representation across different staff groups continues. Postdoc wellbeing advisor have also contributed ideas for wellbeing sessions including a pilot a 'pets as therapy' session in Jan 2022 as a pilot to see whether a similar scheme could be expanded to others | yes | 2024-01-01 | Deputy director HR | To run 2 x Pets as Therapy sessions by June 2023 and Ensure a minimum of 12 wellbeing advisors across the divisions/directorates/staff demographic groups are always trained and available to meet with staff |  | Met - Pets as therapy sessions now incorporated into the Postdoc Association wellbeing initaitives (e.g. every Postdoc Appreciation Week) with good uptake annually. Wellbeing advisors now renamed Wellbeing Champions to clarify their remit and role in signposting support where needed | Postdoc Appreciation Week now embedded as an annual event with the communications team featuring postdocs across ICR social media platforms. The Postdoc Association arrange social and cohort building opportunities to build wellbeing throughtout the year (this has grown from coffee vouchers and socials to film nights with the other staff associations) | No further action
Bullying and harassment
The aims of these obligations are to eliminate bullying and harassment in the research system, tackled through progressive policies and secure mechanisms to address incidents.
ECI3 | Promote a healthy working environment through effective policies and practice for tackling discrimination, bullying and harassment, including providing appropriate support for those reporting issues. | Launch of a new wellbeing action plan planned for early 2023 + associated communications campaign | yes | 2023-12-01 | Deputy director HR | Aim for 75% staff agree that ICR offers support and guidance for mental health and wellbeing and 65% staff felt ICR had taken effective action to tackle bullying and harrassment. Evaluate uptake of the Report and Support tool in first 6 months of use (including anonymous vs non anonymous reporting stats)and launch wider comms following 2023 attitude survey results |  | Not met - 2023 survey results: 69% of postdocs and 71% of group leaders agreed that the ICR provides good guidance and support for mental health and wellbeing which falls a little short of the 75% KPI. We then ran a 'morale' survey in 2025 to explore this topic in greater detail. | In response to 2023 and 2025 survey data, Management Committee have set up the Wellbeing Working Group (includes researcher membership) as a single point to monitor wellbeing in the work place and report its findings to the ICR's senior management via regular reports to the ICR's Health Safety and Environment Committee. The group's first action is to review the newly agreed ICR Wellbeing Strategy and consider priorities for delivery in year one. | Ongoing -ACTION 1 forward action plan
ECM3 | Ensure managers encourage reporting and addressing incidents of discrimination, bullying and harassment. | See ECI6 re introduction and roll out of Report and Support tool at ICR
ECR4 | Ensure researchers use available mechanisms to report staff who fail to meet the expected standards of behaviour in relation to discrimination, harassment and bullying. | See ECI6 re introduction and roll out of Report and Support tool at ICR
Equality, diversity and inclusion
The aims of these obligations are to ensure managers and researchers are trained in-, aware of- and adopt practices enhancing equality, diversity and inclusion.
ECI4 / ECM1 | Ensure managers undertake relevant training and development opportunities related to equality, diversity and inclusion, and put this into practice in their work. | Recuitment training for recruiting managers is now mandatory. Next planned steps are to extend the training to all taking part in interview panels | yes | 2024-12-01 | HR Director /deputy director HR | For EDI guidance on recruitment training and selecting an interview panel to be added to the ePloy e-recruitment system so that recruting managers are able to access the training at the point of needing to advertise new roles. To gather feedback from 3 managers researchers ahead of launching |  | Updated - Action was reviewed and request was for the recruitment training to take place in person, face to face rather than as an e-learning module. It was launched and rolled out in March 2024 | Over 180 line managers have now participated in the training which has received excellent feedback. From this came a request from participants to reinstate Employment Law trainingand ACAS sessions as additional support for managers. Training on the topic will continue to be required to post a vacancies in the new ERP and will be integrated into line manager training offer. | No further action
ECR2 | Ensure researchers act in accordance with employer and funder policies related to equality, diversity and inclusion. | See ECM2
Research Integrity
The aims of these obligations are to ensure managers and researchers are trained in-, aware of- and maintain high standards of research integrity, and are able to report infringements or misconduct.
ECI5 / ECM2 | Ensure researchers and their managers are aware of, and act in accordance with, the highest standards of research integrity and professional conduct. | a) Increase the number of classroom Research Integrity sessions from 3 to 12 times per year to accommodate all new joiners. b) Include RI training to HR probation checklist for all staff by end of 2023 academic year. | yes | 2023-12-01 | RGC/RDM | From April 2023 that all new joiners at the ICR have attended a mandatory Research Integrity training within their first 6 months, and for all faculty to attend the training as a panel member every 5 years |  | Met - Research Integrity training now embedded and running each month to accommodate all new research staff. At least one member of faculty attends each session as a panel member, enhancing their own knowledge in due course. Course is regularly updated with new content and insights shared by group leaders. e.g. updates on themes around generative AI in publication, peer review and contributing to a positive research culture.These themes shape the priorities of our Annual Research Integrity Concordat report submited to UUK (Research Integrity Concordat) | Approx 300 researchers participate in the training each year which is interactive and case study based. They are encouraged to bring their previous experience and 'what works well' examples from their previous workplaces to share with the others. This bank of examples is then added to as a resource on intranet pages to discuss and consider in the annual team-based integrity sessions which are also mandated. | No further action
ECM3 | Ensure managers report and address incidents of poor research integrity. | See ECI6 re introduction and roll out of Report and Support tool at ICR
ECR2 | Ensure researchers act in accordance with employer and funder policies related to research integrity. | See ECM2
ECR4 | Ensure researchers use available mechanisms to report staff who fail to meet the expected standards of behaviour in relation to research misconduct. | See ECM2
Policy development
The aims of these obligations are to encourage all researchers to actively contribute to the development of policies driving positive change at their institution.
EI7 | Consider researchers and their managers as key stakeholders within the institution and provide them with formal opportunities to engage with relevant organisational policy and decision-making. | Embedded into BAU
ECM5 | Encourage managers to engage with opportunities to contribute to policy development aimed at creating a more positive research environment and culture within their institution. | Embedded into BAU
EM5 | Engage with opportunities to contribute to relevant policy development within their institution. | Embedded into BAU
ECR5 | Encourage researchers to consider opportunities to contribute to policy development aimed at creating a more positive research environment and culture within their institution. | Aim to run Above and Beyond awards 2 x per year with at least 25 nominations per round with shortlists and winners widely communicated in internal communications | no | 2025-12-01 | HR Director/ deputy director HR | In 2021 54% staff agreed ICR recognised the hard work and dedication of staff, aim to increase this to 70% in the next pulse surveys 2023 & 2025 |  | Met - 2023 figure for recognition of hard work and dedication of staff decreased to 37%. Above and Beyond awards embedded in the annual calendar with over 100 nominations received in 2025. 2025 pulse survey asked the question 'I feel appreciated for the work I do' which 73% of researchers agreed with. | Follow up focus groups found that this survey question needed to be more specific as to whether it is measuring recogition from line manager or recogition through pay. The link between appraisals and pay was uncoupled in 2024 meaning that the way this question is worded in future surveys will be reviewed to clarify whether it's measuring local recogntion by line manager vs pay | No further action
ER4 | Recognise and act on their role as key stakeholders within their institution and the wider academic community. | Informatics resources and support developed as part of the first DTP cohort to be made available centrally to benefit all researchers at ICR, raising the profile of experts/expertise at the ICR in key areas of informatics and quantitative methods. | yes | 2025-12-01 | DTP manager and RDM | For a faculty informatics network to meet and agree terms of reference and objectives by Dec 25 (senior recruitment in progress) |  | Met - Launch of the Data Science Steering Committee in 2023. Seminar series launched in 2024/2025 academic year with strong attendance + a suite of additional in house training offered on topics included data and software carpentry to better support researchers and build the data science community of researchers - who may be individual experts within different research teams and therefore in need of technical mentors/network. Annual 'carpentries week' now offered by in house experts and seeing strong uptake by researchers | Good engagement from researchers means the seminar/networking series has been renewed for another academic year (2025/2026), providing regular networking opportunities for informaticians to meet others working across different teams and get the support they need from Scientific Computing and Data Science teams which was identified as an organisational area that needed strenthening | No further action
Employment
Recruitment and induction
The aims of these obligations are to ensure recruitment of researchers is open and fair and researchers receive effective inductions into the organisation.
EI1 | Ensure open, transparent and merit-based recruitment, which attracts excellent researchers, using fair and inclusive selection and appointment practices. | Run 2-3 good practice webinars pa around fair and inclusive recruitment (including education on neurodiversity) throughout the year recording these where possible and making them available to managers | yes | 2023-01-01 | Wellbeing & occ. health coordinator/ Deputy Director HR/EDIM | For the webinars/best practice sessions to attract >25 people per session and for the feedback from managers to indicate that these sessions helped them through the recruitment process |  | Updated - In the reporting period a Head of Recruitment was hired who introduced an in person recruitment training in 2024 which has now trained over 180 recruiting managers and received excellent feedback. Off the back on this training, ICR has also reintroduced employment law training in person and a subsequent ACAS training series offered to line managers | Impact of this has been that recruitment training needs to be completed in order to create a job posting on ePloy. Group leaders are being asked for evidence of paricipating in this training by grant funders to either apply for funding or to sit on funding panels, further reinforcing the importance of refreshers on this topic and willingness to participate | Ongoing -ACTION 4 forward action plan
EI2 | Provide an effective induction, ensuring that researchers are integrated into the community and are aware of policies and practices relevant to their position. | i) Monitor our CDF rolling pass rate. ii) Enhance the team leader training to include Introduction to Research Operations in addition to the existing Intro to Research Finance | yes | 2024-01-01 | Research Operations Manager and RDM | Aim for >80% CDF pass rate (rolling average over 5 years) at the next review in Jan 2024. Collect feedback on the new team leader induction sessions when piloted in Feb 2023 and amend content/delivery accordingly |  | Met - 100% pass rate over the last 5 years. Tenure Assessment Process reviewed and approved in 2024. Feedback sought from those who went through the new process e.g. receiving timely written feedback on outcomes. In 2025 the paperwork was aligned to the Readership process to avoid an additional, similar application being required. The CDF network continues to be a thriving peer-peer forum for those going through TAP to share their experiences with those at an earlier stage of the process | Since the introduction of the new process, 6 group leaders successfully be awarded tenure in the last 12 months. 3 new CDF group leaders have joined ICR in that time, attending the CDF forum and meeting those further through their CDF and to hear from key contacts .eg. sessions from HR business partner to discuss some common challenges around recruiting a new team and managing probation. | No further action
Recognition, reward and promotion
The aims of these obligations are to ensure the fair and inclusive recognition of researchers as part of their career progression.
EI3 | Provide clear and transparent merit-based recognition, reward and promotion pathways that recognise the full range of researchers' contributions and the diversity of personal circumstances. | Ways of addressing this to be explored by the Athena swan working group in 2023 | [5 empty] | ICR is working to improve clarity and consistency in pay by defining core salaries, standardising additional payments based on responsibility and experience, benchmarking and revising salaries to remain competitive, and introducing a remunerations committee for specific roles | Develop a deeper understanding of pay gap locations (by function and level) and causes. Comprehensive report detailing pay gap locations (by function and level) and underlying causes to ESG by December 2025. Where gaps of over 10% are found, review whether there is a difference by gender in starting salary (Source - Athena SWAN 2025) | Ongoing -ACTION 5 forward action plan
EM3 | Managers commit to, and evidence, the inclusive, equitable and transparent recruitment, promotion and reward of researchers. | Ways of addressing this to be explored by the Athena swan working group in 2023 | [5 empty] | As part of our 2025 Athena SWAN submission we have gathered data on gender of applicants at different grades compared to hires to enable us to spot patterns/trends emerging and put measures in place to address these | The goal is to achieve 100% uptake of inclusive recruitment training by 2029, alongside the implementation of additional support materials to enhance consistency across hiring practices (source is the 2025 Athena SWAN submission) | Ongoing -ACTION 4 forward action plan
Responsibilities and reporting
The aims of these obligations are to ensure that researchers and their managers understand and act on their obligations and responsibilities.
EM2 | Managers familiarise themselves, and work in accordance with, relevant employment legislation and codes of practice, institutional policies, and the terms and conditions of grant funding. | See EI2 re: enhanced team leader induction being rolled out to highlight processes and policies managers of researchers need to be aware of. Training open to all team leaders joining the ICR at ICR fellow level and above | yes | 2024-01-01 | Research Operations Manager and RDM | Collect feedback on the new team leader induction sessions when piloted in Feb 2023 and amend content/delivery accordingly - extend training to existing managers at group leader or equivalent level who have not yet attended and could benefit from knowledge of grant funding processes and procedures |  | Updated - A full induction programme was developed to introduce key research support services in addition to grants and finance. Split sites, the large number of subject matter experts and the small numbers of new faculty joining ad hoc throughout the year means that we paused these sessions and will instead exploit the Learning Management System within the ERP to deliver this content to new group leaders asynchronously/on demand with the option for them to arrange follow up conversations as needed | Consultation with new group leaders found that a growing number of topics were considered essential to include in the induction, making it logistically more complicated to organise. With the new LMS we now have the possibility to transform these presentations into SCORM packages to form an on-demand induction programme for group leaders to view when they first join. It also means that the content is also available to revisit and/or can be updated in response to feedback and periodically refreshed, keeping the information current | Ongoing -ACTION 6 forward action plan
ER1 | Researchers ensure that they work in accordance with, institutional policies, procedures and employment legislation, as well as the requirements of their funder. | See ECI5 re: Introduction of mandatory Research Integrity training for all staff | yes | 2023-12-01 | RGC/RDM | From April 2023 that all new joiners at the ICR have attended Research Integrity training within their first 6 months and faculty joining the panel once every 2-5 years |  | Met - The interactive course has been delivered monthly either in person or online since January 2023. We have seen strong willingness by group leaders to endorse the programme and share their insights with participants, enriching the topics and case studies covered with each iteration. Evidence of course attendance is needed at the 6 month probation check meaning that all researchers are attending | We will use the new ERP 'Learn' module to build this as a hybrid course so that the pre-course work and some of the information in the session can be delivered beforehand, and enable us to extend the case study discussions in the in person session to cover a greater number of topics. After each session we ask the faculty panel to suggest any changes/improvements and incorproate these into the subsequent delivery. Group leaders will periodically share articles of interest for inclusion in the course, showing their willingness to keep the content relevant and meaningful | No further action
ER2 | Researchers understand their reporting obligations and responsibilities. | See ECI6 re introduction and roll out of Report and Support tool at ICR | yes | 2023-12-01 | Deputy directors HR | Aim for 75% satisfaction with support for wellbeing and mental health support and 70% feeling effective tackling of B&H in the next all staff survey planned for spring 2023. Additional question for 2023 to establish the proportion experiencing B&H within the last 12 months and be able to report these figures by division/directorate to help support group leaders in addressing concerns |  | Not met - Both of these figures decreased in the 2023 survey - by 4 and 6% points respectively amongst postdocs and group leaders. Since then, the ICR has purchased a new Employee Assistance Programme offering a huge suite of on demand resources and support with wellbeing topics as well as online chat and helpline. In response to staff feedback the EAP link is pinned to the top of the intranet homepage, making it easy for all to find and access. The 2025 survey included the question: I have the support I need when work feels difficult or stressful, 67% of postdocs and 78% research leaders agreed | In response to survey data, Management Committee have set up the Wellbeing Working Group as a single point to monitor wellbeing in the work place and report its findings to the ICR's senior management via regular reports to the ICR's Health Safety and Environment Committee. The group's first action is to review the newly agreed ICR Wellbeing Strategy and consider priorities for delivery in year one. | Ongoing -ACTION 1 forward action plan
People management
The aims of these obligations are to ensure that researchers are well-managed and have effective and timely performance reviews.
EI4 | Provide effective line and project management training opportunities for managers of researchers, heads of department and equivalent. | With increased messaging around importance of 10 days professional development opportunities as per Researcher Concordat - aim to see an increase staff attitude survey scores for "my immediate manager supports my personal development. Draft bid for a Learning Management System. Scope project manangement training resources to make available to line managers/group leaders | yes | 2023-12-01 | HOD | Increase score for my line manager supports my personal development from 82% in 2021 to 85% in the 2023 pulse survey. Look at differences by division/directorate to be able to target professional development resources & researcher concordat communications. Submit bid for Learning Management System by July 2023 |  | Met - In the 2023 survey 91% of staff agreed that they had a good working relationship with their line manager. 73% of staff say they are given good training to perform their role, this increased to 83% amongst postdoc and equivalent grades. Results were also analysed by division as per the action. In 2025 the ICR developed a CPD policy mandating 10 days of professional development for all staff - building on the successful introduction of development time for postdoc and equivalent grades from 2020. | A Researcher Concordat section now exists on the ICR appraisal form so researchers and their managers must review and plan the 10 days of training as part of the appraisal discussion. Now in it's 5th year, we receive very few queries about the process and surveys show that the majority of researchers now plan and take 10 days of development time per year. This hashelped to establish a strong precendent for a professional development focus at appraisal and will help with widening this to all scientific staff via a CPD policy | No further action
EI5 | Ensure that excellent people management is championed throughout the organisation and embedded in institutional culture, through annual appraisals, transparent promotion criteria, and workload allocation. | Updated "Developing your People" brochure to be updated annually ahead of the appraisal window to encourage managers to maximise internal and external development programmes. Aim to continue to increase satisfaction with appraisal based on positive increase seen in 2021 | yes | 2023-12-01 | HOD | To see at least 12 nominations for the future leaders programme running in Spring 2023. To see satisfaction with appraisal increase from 75% in 2021 to 80% in 2023 staff attitude survey |  | Partially met/updated - The Future Leaders programme continues to run annually (at least 12 per cohort) and has been expanded to include participants from our partners at Royal Marsden to promote joint working and knowledge exchange with applications seleted by a panel of senior leaders. Satisfaction with appraisals showed a very marked decrease in the 2023 survey (21% decrease). Organisationally it was therefore decided to ammend the appraisal process and replace with a professional development review not linked to pay | To support the professional development focus for the 2025 appraisal round, L&OD compiled a 'developing your team brochure'. At the request of researchers, this was shared appraisees and line managers to help all parties consider the development opportunities available and to help them prepare well for their professional development reviews. The appraisal process is being redesigned as part of the new ERP implimentation and satisfaction will be measured again after that is in place | No further action
EM1 | Managers undertake relevant training and development opportunities so that they can manage researchers effectively and fulfil their duty of care. | see ECM3 re: duty of care and Wellbeing policy
EM4 | Managers actively engage in regular constructive performance management with their researchers. | Embedded into BAU
ER3 | Researchers positively engage with performance management discussions and reviews with their managers. | For HR to continue to run >3 appraisal training sessions ahead of every appraisal window to capture all new managers and those new to the ICR. Circulate supporting resources for appraisees (recording) ahead of appraisals too. | yes | 2025-12-01 | Deputy Director HR/HOD | To see at least 20 managers attending these appraisal training sessions per year and for attitude survey scores for researchers being satisfied with their appraisals to increase to 75% for 2023. |  | Updated - In 2025 the appraisal process was uncoupled from pay award. Guidance documentation was prepared and made available centrally together with a 'developing your people' brochure with internal and external opportunities for different staff groups highlighted. A new appraisal system is being designed as part of ICR's ERP implementation - this will enable professional development and goals to be accessible, visible and more easily tracked by researchers and their managers. | From 2027, the appraisal process will launch as part of a wider 'Talent' module in the new ERP and once embedded satisfaction can be remeasured | No further action (to review after ERP roll out)
Job security
The aim of this obligation is to improve the job security of researchers.
EI6 | Seek to improve job security for researchers, for example through more effective redeployment processes and greater use of open-ended contracts, and report on progress. | Due to pandemic this action was not progressed by the working group however it will be the main topic for 2023/4 agenda including how to offer better guidance to managers on offering contacts for the full duration of funding wherever possible to encourage good recruitment practice | no | 2025-12-01 | Deputy Director HR | Create an SOP for HR advisors and managers & guidance for hiring managers re: offering contacts for the full length of the funding available wherever possible with managers asked to provider a reason if this is not possible |  | Due a high turnover of operational HR staff and the move to the new ERP, developing an SOP has been paused as item as the whole employee cycle is being reviewed and redesigned as part of the ERP implimentation |  | No further action
Professional and Career Development
Championing professional development
The aims of these obligations are to promote the importance of professional development and ensure researchers have the time to engage in it.
PCDI1 | Provide opportunities, structured support, encouragement and time for researchers to engage in a minimum of 10 days professional development pro rata per year, recognising that researchers will pursue careers across a wide range of employment sectors. | Continue to send communications & codes of practice around Concordat expectations to both researchers and their managers with clear expectation for training time to be planned and discussed as part of the appraisal. From 2023 onwards include data on the range of career destinations of postdoc leavers and where researchers can get additional support from outside their immediate teams e.g. promoting the L&OD function and external careers support | yes | 2024-04-01 | RDM/Faculty Champion for Researcher Concordat | Supplimenting the comms from Jan 2023 to include data on the next employement of researchers to manage expectations and further faciliate training and career development conversations. Impact will be around number of researchers surveyed who feel able to take a minimum of 10 days per year (aim for 50% by 2024, currently 15%) aim to increase the number of researchers who feel suffienciently trained to develop their career at ICR or externally from 71% to 80% |  | Met - KPI was met as by 2024, >60% of postdoc and equivalent grades were taking 10 days of training. KPI around feeling sufficiently trained to develop their career at the ICR or externally saw a slight decrease to 68% amongst postdocs. This may be impacted by the wording of the question as postdocs are actively encouraged to develop their careers beyond rather than within the ICR. In the 2025 morale survey 92% of postdoc and equivalent grades felt 'motivated to do their best work' | Postdoc Association were invited to present at the ICRs Board of Trustees in 2024. As a result the ICR began a process of recruiting and appointing a member of faculty to be the inaugural Postdoc Dean to oversee this group of researchers and their career development. The ICR has communicated the 3 areas that the Dean will progress in year one of their appointment in our internal newsletter and at all staff CEO briefing (Oct 2025) | Ongoing -ACTION 7 forward action plan
PCDI6 | Monitor, and report on, the engagement of researchers and their managers with professional development activities. | Continue to promote and facilitate mentors for all CDF and ICR fellows during quarterly meetings to ensure that all have someone identified and a record kept | yes | 2023-06-01 | RDM/Faculty Champion for Researcher Concordat | For 100% of the CDF and fellows to have identied a mentor outside of their own division by May 2023 |  | Met - Reminders are sent at 12 months if no mentor has yet been nominated so that all going to midterm have a nominated mentor. In addition the Academic Dean meets 1:1 with all new CDF across both sites. In 2025 guidance for mentors and mentees was updated to offer more clarity around expectations on both parties | Mentors/mentee pairings are tracked centrally and both provided with expectations and guidance. This ensures mentors are invited to mid terms and NTL assessments to additionally continuity. | No further action
PCDM3 | Managers allocate a minimum of 10 days pro rata per year, for their researchers to engage with professional development, supporting researchers to balance the delivery of their research and their own professional development. | See PCDI1 - Postdoc codes of practice now updated to highlight manager's role in faciliating this but currently only 15% researchers feel able to engage in the full 10 days per year. Appraisal paperwork also asks researchers to indicate if they have not been able to take up the 10 days to encourage that it's expected | yes | 2024-08-01 | RDM/Faculty Champion for Researcher Concordat | In 2021 only 15% of ICR researchers reported taking the full 10 days allocation (in line with national CEDARS figures) Aim for this to increase to 50% by July 2024 with 100% of researchers able to take 5-9 days professional development per year. Communication of the importance of professional development and the Concordat at the annual postdoc retreat to n=60 |  | Met - by 2024, >60% of postdoc and equivalent grades were taking 10 days of training. Researcher Concordat expectations are also highlighted in the Postdoc Codes of Practice shared with all new starters and annually at the postdoc away days or careers conferences (which have taken place annually since the last submission to 50-70 postdoc grades). Faculty have also been reminded of 10 days of professional development as part of the relaunched (in person) Supervisor training (attended by 90 in 2024/2025) and also as part of a presentation by Postdoc Dean on supporting Early Careers at the 2025 Faculty Retreat (~75 faculty in attendance) | Postdoc codes of Practice reviewed and updated by Academic Board in Jan 2025. Updates included ensuring a definition of 'postdocs' is given which includes those grades equivalent to Postdoc Training Fellows e.g. analytical scientist and statistician grades. Distribution groups were refreshed in June 2025, increasing the number of ECRs receiving relevant development opportunities. Next steps are to develop a structured training plan for the postdoctoral period which also meets the needs of full spectum of postdoc equivalent grades (wet and dry lab) | Ongoing -ACTION 7 forward action plan
PCDR1 | Researchers take ownership of their career, identifying opportunities to work towards career goals, including engaging in a minimum of 10 days professional development pro rata per year. | The evaluation of the Steps to Fellowship success programme was presented at Vitae Conference in 2021. Proposal to continue to monitor award success for both cohorts but over a longer time point to account for pandemic and also preparation time needed for delegates | yes | 2024-01-01 | RDC | For submission rates to be monitored and reported at Jan 24 Academic Board and adjust programme timings accordingly for the next cohorts taking part |  | Updated - Steps to fellowship success programme was paused due to organisational changes with the NIHR delivery partners. ICR and our Biomedical Research Centre have continued to run Pathway to Independence for clinical researchers (2024 and 2025) and an monthly Application Development Forum to support those applying for their own research funding | The 2 distinct programmes offer a higher degree of flexibility for participants (monthly opt-in sessions over a 12 month period vs 3 day residential), this saw an increased uptake from Allied Heath Professionals, a key target group within the BRC strategy. The two most recent Pathway to Independence programmes were open to nurses and AHPs to support their transition to research careers | No further action
Career development reviews
The aims of these obligations are to ensure researchers and their managers are engaging in productive career development reviews.
PCDI2 | Provide training, structured support, and time for managers to engage in meaningful career development reviews with their researchers. | To include careers destination info in the pre-appraisal memo sent to researchers and managers (highlighting concordat requirements). To better promote new postdoc sessions to managers as we use these sessions to talk about professional and career development .e.g. how to make the most of the LinkedIn alumni group, L&OD and availabilty of career 1:1 appointments | yes | 2024-12-01 | RDM | For at least 80% of postdocs to feel they are given the training and support they need to develop their careers at the ICR or externally and maintain appraisal completion rates at 100% . Option to look at differences in support by division to be able to offer targeted input e.g. postdoc guide and developing your people guides. |  | Not met - A decrease of 3% in the number of postdocs who say they get the training and support to develop careers at the ICR or externally. The postdoc association was asked to present to the ICR Board of Trustees in Nov 2024 which is now a standing item to ensure postdocs have a voice in this key forum | Following the first postdoc paper to Board of Trustees in 2024, the ICR identified and appointed a Postdoc Dean. They started in Sept 2025 with a goal to put in place a strutured programme of support for this group including more opportunities to network and build links with postdocs at other organisations to help them develop their onward careers | Ongoing -ACTION 7 & 8 forward action plan
PCDI6 | Monitor, and report on, the engagement of researchers and their managers with researcher career development reviews. | Appraisal completion rates are tracked by HR and auto reminders sent out ahead of cut off. Satisfaction with the quality of appraisals is then measured in the staff attitude survey and analysised by job type and other key demographics (e.g. gender, division) | yes | 2024-06-01 | Deputy director HR | For satisfaction with appraisals among postdocs to remain >75% and that satisfaction with training and career advice given to develop internally or externally would increase from 71% to 80% amongst this group by June 2024 |  | Not met - Satisfaction with appraisals universally decreased in 2023 survey amongst all staff groups (between -11 to -33% points). Satisfaction with training and career support however was met. | The survey results meant that leadership took the decision in 2024 to uncouple appraisal outcomes from pay. The introduction of a new ERP in 2026 means the appraisal system needs to be reviewed and integrated into the people workflows meaning this question won't be asked again in a survey until the new system is in place | Ongoing -ACTION 9 forward action plan
PCDM1 | Managers engage in regular career development discussions with their researchers, including holding a career development review at least annually. | see EI5 re brochure to support managers. Include a new question in the annual training survey to determine whether researcher are having regular career development conversations with their managers as opposed to only as part of the annual appraisal process | yes | 2024-12-01 | RDM | Aim for a benchmark of 50% of researchers completing the annual training survey have having career development discussions with their manager beyond once a year in their appraisal (new question added from 2023 onwards) |  | Partially met - At the request of researchers, from 2024, the 'developing your team' brochure was shared with all staff to help managers and appraisees prepare well for appraisals. Responses to the annual training survey continues to inform the annual training offer (though the KPI of 50% of researchers filling this in was not met). An annual paper to academic board in January outlines the training plans/priorities which will is co-developed with the Postdoc Association and from Jan 2026 also with the Postdoc Dean | Introduction of the new LMS in Sept 2026 will make it easier for users to search courses/resources on demand andfor the training team to more closely monitor areas of greatest interest/uptake and shedule additional content as required | No further action
PCDR4 | Researchers positively engage in career development reviews with their managers. | Appraisal training is mandatory for managers of researchers and delivered annually ahead of appraisal window but is not aimed at appraisees. From 2023 onwards provide a recorded session or 'lunch and learn' for researchers on "making the most of your appraisal" in response to feedback from the Scientific Officer Association | yes | 2024-01-01 | RDM/RDC | To co-develop the session with SOA and have at least 20 attendees at this session with 100% of attendees finding the session helpful and would recommend to others. Maintain postdoc satisfaction with appraisals at >75% with continued comms for them and managers on planning and recording 10 days training |  | Met - The SOA training session was designed to help individuals prepare for their appraisal (including SMART goal setting) and was universally well recieved. However satisfaction with the overall appraisal process universally decreased in 2023 survey amongst all staff groups (between -11 to -33% points). | The survey results meant that leadership decided to uncouple the 2024 and 2025 appraisal rounds from pay award, meaning that the SOA support session was also paused . The introduction of a new ERP (expected launch Sept 2026), means the whole appraisal system will need to be reviewed and integrated into pre-set workflows (adopt, not adapt). | Ongoing -ACTION 9 forward action plan
Career development support and planning
The aims of these obligations are to promote researchers' career development planning through tailored support and gathering evidence of professional experience.
PCDI3 | Ensure that researchers have access to professional advice on career management, across a breadth of careers. | Restart the Pathway to Independence programme for clinicians in Autumn 2023 once again in partnership with BRC. Explore the next desinations of the 2019 and 2021 Pathways cohorts to assess the impact of pandemic on % going onto team leader roles vs those taking on leadership roles in industry | yes | 2024-12-01 | RDM/RDC | Run a Pathways clinical programme with at least 20 participants from a mix of national BRCs and that 90% would recommend this programme to others. Report on the next destinations of the non clinical Pathways programme + postdoc next destinations to academic board in Jan 2024 |  | Met - Clinical Pathways programme was run in Jan 2024, attracting a mix of 24 cancer research clinicians from across different BRCs and funders. A follow up session was run after 12 months to offer additional support where needed and found that the majority of those in the follow up session had secured some grant or project funding but were still too early stage to have applied for Clinician Scientists or equivalent independent roles. Periodic tracking next destination of participants is embedded. | Feedback from the Jan 2024 run of the programme meant there was strong support to embed this programme biennially in BRC buget. It ran again in Nov 2025, once again open to participants from a wide range of cancer BRCs including nurses/AHPs, resulting in additional NIHR contacts to run other activities together in the interim | No further action
PCDR3 | Researchers maintain an up-to-date professional career development plan and build a portfolio of evidence demonstrating their experience, that can be used to support job applications. | To include a PDP/record keeping element of the new LMS spec being scoped by L&OD in 2023 and liaise with HR oprations re: any new appraisal software to ensure a joined up approach to training and monitoring of appraisal objectives. Ask members of staff associations to input into the needs/usability of this element | yes | 2024-06-01 | Learning & Org. Development Programme Coordinator | For reps from multiple staff associations to have been consulted on any PDP element to ensure usability for them in any proposed LMS, incorportating their feedback into the spec |  | Updated - This approach was superceded by the purchase of a large ERP from a new provider which will include a Talent and Learn modules where researchers and their managers will have the ability to record internal and external training and development opportunities within their user profile. | One single system which is being "adopted not adapted" removes the need for integrating different systems. Researchers will be engaged in user testing and demos with clear guides being produced by the change team ahead of launch | No further action
Research identity and leadership
The aims of these obligations are to provide researchers with opportunity to progress in their careers by developing their research identity and leadership capabilities.
PCDI4 | Provide researchers with opportunities, and time, to develop their research identity and broader leadership skills. | Run a 2023 Pathway to Independence clinical and non clinical programme incorporating the learning from having run online to explore hybrid delivery to accommodate schedules and promote inclusion for those not able to attend fully residential | yes | 2024-12-01 | RDM and RDC | For both programmes to see at least 20 participants joining from across different research organisations and for any new formats (e.g. hybrid) to be evaluated fully to undertand whether they help or hinder the high satisfaction scores. |  | Met - 2023 Pathways programme was a hybrid structure with in person and online sessions. In reponse to participant feedback we have consolidated the 2025 programme to return to fully residential (n25 and n27 respectively) with an online follow up session. Retaining a unique in person-residential element was acknowledged as central to the programme's success since it began over 10 years ago | Selections for the 2025 programme were competitive across all participating institutions. The ICR panel selected a balance of research areas, diversity and inclusion characteriscs. Overall 80% of 2025 programme participants were women. We have now embedded the monitoring of next destinations of programme participants, consistently seeing ~55% securing group leader roles within 3 years of participating | No further action
PCDM4 | Managers identify opportunities, and allow time (in addition to the 10 days professional development allowance), for their researchers to develop their research identity and broader leadership skills, and provide appropriate credit and recognition for their endeavours. | Ways of addressing this to be explored by the Concordat working group in 2024 once robust uptake of the 10 days can be shown | yes | 2024-12-01 | RDM and Faculty Champion for Researcher Concordat | Aim for >50% uptake of 10 days before working group reviews how best to promote to managers |  | Met - 2024 uptake: >60% of postdoc and equivalent grades taking up the full 10 days of prof development. Highlight this requirement to managers and researchers ahead of each appraisal window opening and send updated copies of the 'developing your people' brochure and giving examples of practical development oppotunities to consider. | The roll out of the 10 days development with postdoc and equivalent grades has formed the basis of a new CPD policy (due for approval in late 2025). Using the lessons learnt from Concordat implementation, the emphasis to managers will be on identifiying the best ways of meeting the specific training needs (e.g. through work shadowing, mentoring or external networks - as well as traditional training offerings) | Ongoing -ACTION 7 forward action plan
PCDM5 | Managers engage in leadership and management training to enhance their personal effectiveness, and to promote a positive attitude to professional development. | Second cohort due to complete senior leadership programme by Dec 23. Monitor impact of the training on Faculty in the 2023 staff survey and communicate results to leadership to inform future direction of programme | yes | 2023-12-01 | HOD | Aim for 65% of team leaders feel they have the training needed to perform their jobs in the 2023 staff survey. Extend EMBO training to at least 3 researchers who manage labs and set research culture day to day e.g. the senior staff scientist cohort |  | Met - EMBO places systematically extended to senior staff scienist grades since 2021. In 2023 survey, 73% of research group leaders believe they are given good training to perform their current job. Via the CDF network we know that those attending EMBO say it would be helpful to attend a refresher a couple of years later, particularly where they attended the programme very early in their CDF tenure | In response to researcher feedback, EMBO follow up sessions now made available through partner research institutes network on a range of topics including influencing and negotiation. Supervisor training has also been refreshed for all supervisors in 2024/2025 academic year - in person rather than online with a lunch provided to encourage practice sharing and community building - feedback included that this was one of the most useful courses the faculty had attended. This refresher is now mandated every 4 years rather than every 5 years as it was previously | No further action
PCDR5 | Researchers to seek out, and engage with, opportunities to develop their research identity and broader leadership skills | Postdoc Association request for an annual Strengthscope session for postdocs to bridge leadership and career development and support 10 days professional development training - from Jan 2023 and reviewed annually. Continue inviting 10 postdocs a year to attend Leadership course at Royal Soc Biology | yes | 2024-01-01 | RDM/PDA | For 10 postdocs to attend the strengthscope pilot session and for >90% to say they would recommend it to a colleague |  | Partially met - The Postdoc Association members were invited to the Strengthscope session - 7 attended and all gave positive feeback that it gave them some actionable feedback to enhance their personal development | Postdoc association now include a team-building or professional development activity annually as part of their budget allocation | No further action
Diverse careers
The aims of these obligations are to recognise, value and prepare researchers for the wide range of career options available to them within and beyond research.
PCDI5 | Recognise that moving between, and working across, employment sectors can bring benefits to research and researchers, and support opportunities for researchers to experience this. | Working with the Business and Innovation manager and Head of Stategic communications to promote the Industry training and collaboration fund to all ICR team leaders ahead of appraisal window 2023 | yes | 2024-01-01 | BIO business development manager/ RDM | For three expressions of interest in using the training funds to be received by Jan 2023 with further promotions planned if this is not met |  | Updated - Despite numberous communications, there were no expressions of interest to the fund researchers using this scheme. Instead in 2025 ICR supported researchers of all grades to participate in the Your Entrepreneur Scheme (YES) this was taken up by 7 participants. A full evaluation conducted revealing some areas where adidtional support will be useful in subsequent years | In addition to offering funded places on the YES scheme, Business and Innovation have involved the ICR's Entrepeuneurs in Residence in the programme delivery, with them offering mentoring to those participating. | No further action
PCDM2 | Managers support researchers in exploring and preparing for a diversity of careers, for example, through the use of mentors and careers professionals, training, and secondments. | see PCDI1 - Ciculate postdoc codes of practice together with "developing your people" resource and alumni destination data for managers each January ahead of appraisal windown | yes | 2024-01-01 | RDM/RDC | Maintain postdoc appraisal statisfaction at >75% in attitude survey scores & monitoring and reporting on the number of staff being put forward for development programmes |  | Not met - Whilst appraisal statisfaction scores decreased across all staff groups in the 2023 attitude survey, there has been a record interest in applicants for the 2025 Pathway to Independence programme meaning that additional places were secured to be able to send 8 rather than 6 postdocs | Postdoc Dean and selection panel commented on the high quality of the applications and offered 8 places. There continues to be strong uptake for other Postdoc Leadership courses offered including 'Leadership in a Lab' - applicable to those wanting an academic or industry role. Postdoc Dean to further structure & communicate the support offered to postdocs and guidance given to their line managers - including a presentation to all faculty at the 2025 faculty retreat attended by ~75 group leaders | Ongoing -ACTION 7 forward action plan
PCDR2 | Researchers explore and prepare for a range of employment options across different sectors, such as by making use of mentors, careers professionals, training and secondments. | To ensure Thinking Ahead sessions remains a sustainable programme we will add additional members to the organising panel to ensure a critical mass of 3 postdocs for arranging and hosting these talks. Continue to run three sessions per year and record these (as far as speakers will allow) to make the content available to a larger audience on demand | yes | 2024-06-01 | RDM/PDA | Recruit 2 attitional members to the organising committee and continue to have >15 postdocs attending each quarterly |  | Updated - Postdocs are sent the postdoc codes of practice when they join the ICR setting out the expectations around 10 days of training and professional development time. They are encouraged to plan ahead and join the Postdoc Alumni Linked In group (over 300 members) as a source of mentors and contacts outside the organisation. Alumni are invited back at annual postdoc careers conferences to share their knowledge with current postdocs | Full postdoc training programme shared with the new Postdoc Dean to enable a gap analysis. Their year 1 focus on postdoc networking opportunities to offer more agency in building the next steps of their career. The ICR continues to offer a range of careers webinars and ~80 x 1:1 meetings with Careers Consultants throughout the year, the latter of which are consistently booked up by postdocs and students | Ongoing -ACTION 8 forward action plan
PCDR6 | Researchers consider opportunities to develop their awareness and experience of the wider research system through, for example, knowledge exchange, policy development, public engagement and commercialisation. | Aim for 3 postdoc-lead Thinking Ahead sessions pa. to highlight the wider research ecosystem and the career possibilities available as well as the scope to maximise ICR alumni Linkedin group | yes | 2023-12-01 | RDM/PDA | Run a postdoc careers conference attended by at least 65 by June 2023 achieving >80% would recommend the event to colleagues |  | Met - Postdoc Association Careers Conference and Away Day alternate and run in 2024 and 2023 respetively. Feedback gathered and suggestions captured and implemented for the following year. | Following the introduction of a postdoc association presentation to Board of Trustees, board members suggested a range of their own contacts as external speakers, including a keynote who had been at the ICR may years before. In the feedback several participants commented on the range of careers and speakers covered at the event that they would not have otherwise had a chance to meet with e.g. life science investment. Postdocs have been asked to present to the board now annually as a standing item | Ongoing -ACTION 8 forward action plan
* The Researcher Development Concordat defines researchers as individuals whose primary responsibility is to conduct research and who are employed specifically for this purpose by a higher education institution or research institute. The primary audience is research staff, e.g. postdoctoral researchers, research fellows, research assistants. The Researcher Development Concordat encourages institutions to include other groups who actively engage in research as beneficiaries of their Concordat action plan. These could be postgraduate researchers; staff on teaching and research, or teaching contracts; clinicians; professional support staff; technicians.
Further hyperlinks and supplementary information (more rows can be added) |  |  |  |  | Abbreviations and glossary (more rows can be added)
[5 empty] | AHP | Allied Health Professionals
1 |  |  |  |  | BRC | Biomedical Research Centre
2 |  |  |  |  | DTP | Doctoral Training Partnership
3 |  |  |  |  | CDF | Career Development Faculty
[5 empty] | EAP | Employee Assistance Programme
4 |  |  |  |  | EDI | Equality Diversity and Inclusion
5 |  |  |  |  | EDIM | Equality Diversity and Inclusion Manager
6 |  |  |  |  | ECR | Early Career Researcher
[5 empty] | ERP | Enterprise Resource Planning
7 |  |  |  |  | HOD | Head of Organisational Development
[5 empty] | LMS | Learning Management System
8 |  |  |  |  | PDA | Postdoc Association
9 |  |  |  |  | PDP | Personal Development Plan
10 |  |  |  |  | RI | Research Integirty
11 |  |  |  |  | RDC | Researcher Development Coordinator
12 |  |  |  |  | RDM | Researcher Development Manager
13 |  |  |  |  | SOA | Scientific Officer Association
14 |  |  |  |  | SOP | Standard Operating Procedure
15 |  |  |  |  | TAP | Tenure Assessment Panel
16
17
18
19
20

## Funders' obligations
| HREiR Action plan template (add dates) | [6 empty] | Add institutional logo
Details
| Institution name: |  |  |  |  | The institutional audience* for this action plan includes (only include direct beneficiaries; complete or delete, as appropriate):
| Cohort number: |  |  |  |  | Audience (direct beneficiaries of the action plan) |  | Number of | Comments
| Date of submission: |  |  |  |  | Research staff
| Institutional context: |  |  |  |  | Postgraduate researchers
Research and teaching staff
Teaching-only staff
Technicians
Clinicians
Professional support staff
Other (please provide numbers and details):
Complete for submission | [7 empty] | To be completed only when reporting on action plan
| Obligation | Action | Carried over from previous action plan? | Deadline | Responsibility | The targeted impact of the action (success measure) | Comments (optional) | Progress update | The actual impact of the action (reporting against the success measure) | Outcome (ongoing/carried forward/no further action)
Environment and Culture
Awareness and engagement
The aims of these obligations are to work towards an open and inclusive research culture, and to ensure broad understanding and awareness of this amongst researchers.
ECF1 | Including requirements which promote equitable, inclusive and positive research cultures and environments in relevant funding calls, terms and conditions, grant reporting, and policies
Wellbeing and mental health
The aims of these obligations are to champion positive wellbeing amongst researchers, both through appropriate training and enabling new ways of working.
ECF2 | Consider how funding opportunities and policies can facilitate different patterns and ways of working, and promote the wellbeing and mental health of researchers
Equality, diversity and inclusion
The aims of these obligations are to ensure managers and researchers are trained in-, aware of- and adopt practices enhancing equality, diversity and inclusion.
ECF3 | Ensure that funding call requirements and selection processes offer equality of opportunity between different groups of researchers, recognise personal contexts, and promote positive research cultures and working conditions
Employment
Job security
The aims of these obligation are to improve the job security of early career researchers.
EF1 | Include requirements which support the improvement of working conditions for researchers, in relevant funding calls, terms and conditions, grant reporting, and policies
EF2 | Review the impact of relevant funding call requirements on researchers' employment, particularly in relation to career progression and lack of job security
EF3 | Support institutions to develop policies and frameworks to promote sustainable employment arrangements and enhance job security, and provide opportunities for career progression
EF4 | Consider the balance of their relevant funding streams in providing access to research funding and its impact at all career levels
Professional and Career Development
Championing professional development
The aims of these obligations are to promote the importance of professional development and ensure researchers have the time to do so.
PCDF1 | Incorporate specific professional development requirements in relevant funding calls, terms and conditions, grant reporting, and policies. This should include researchers' engagement in a minimum of 10 days' professional development pro rata per year, and evidence of effective career development planning
PCDF2 | Embed the Concordat Principles and researcher development into research assessment strategies and processes
Diverse careers
The aims of these obligations are to recognise, value and prepare researchers for the wide range of career options available to them within and beyond research.
PCDF3 | Acknowledge that a large proportion of the researchers they fund will move on to careers beyond academia, and consider how they can encourage and support this within their remit
* The Researcher Development Concordat defines researchers as individuals whose primary responsibility is to conduct research and who are employed specifically for this purpose by a higher education institution or research institute. The primary audience is research staff, e.g. postdoctoral researchers, research fellows, research assistants. The Researcher Development Concordat encourages institutions to include other groups who actively engage in research as beneficiaries of their Concordat action plan. These could be postgraduate researchers; staff on teaching and research, or teaching contracts; clinicians; professional support staff; technicians.
Further hyperlinks and supplementary information (more rows can be added) |  |  |  |  | Abbreviations and glossary (more rows can be added)
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## Guidance
| HREiR Action plan template (add dates) | [6 empty] | Add institutional logo
Details
| Institution name: | Enter relevant information |  |  |  | The institutional audience* for this action plan includes (only include direct beneficiaries; complete or delete, as appropriate):
| Cohort number: | Enter relevant information |  |  |  | Audience (direct beneficiaries of the action plan) |  | Number of | Comments
| Date of submission: | Enter relevant information |  |  |  | Research staff |  |  | These are your primary beneficiaries, and should be prioritised across the action plan - both by being targeted with actions and evaluated through success measures.
| Institutional context: | Enter relevant information that helps frame the action plan and the intended institutional audience. For example, this box can be used to disclose the research intensiveness of the institution, providing a justification for the breadth/depth of the actions disclosed. |  |  |  | Postgraduate researchers
Research and teaching staff
Teaching-only staff
Technicians
Clinicians
Professional support staff
Other (please provide numbers and details):
Complete for submission | [7 empty] | To be completed only when reporting on action plan
| Obligation | Action | Carried over from previous action plan? | Deadline | Responsibility | The targeted impact of the action (success measure) | Comments (optional) | Progress update | The actual impact of the action (reporting against the success measure) | Outcome (ongoing/carried forward/no further action)
Environment and Culture
Awareness and engagement
The aims of these obligations are to work towards an open and inclusive research culture, and to ensure broad understanding and awareness of this amongst researchers.
ECI1 | Ensure all relevant staff are aware of the Concordat.
ECI2 | Ensure institutional policies and practices relevant to researchers are inclusive, equitable and transparent, and are well-communicated to researchers and their managers.
ECI6 | Regularly review and report on the quality of the research environment and culture, including seeking feedback from researchers, and using the outcomes to improve institutional practices. | Describe here your actions/interventions for meeting the obligation, referring to actions elsewhere in the action plan if preferred. | Has the action been carried forward from a previous action plan? "yes" / "no" | Indicate a month and year | Name all key parties responsible for the action(s) and success measure(s) | Describe here your success measure(s), used to report against the intended impact for researchers and incorporating researchers' views wherever possible. | Describe here any supplementary information. | Describe here a written summary of the progress made against the obligation, taking a broad view of the people and/or organisational development that may have occurred. | Provide evidence that directly reports against all success measures described previously. | Indicate the next steps for the action from the following options: "ongoing" (if the deadline is scheduled in the future), "carried forward" (if the action was not completed as planned by the initial deadline) or "no further action" (accompanied by a brief explanation).
ECR1 | Encourage researchers to actively contribute to the development and maintenance of a supportive, fair and inclusive research culture and be a supportive colleague, particularly to newer researchers and students.
ECF1 | Including requirements which promote equitable, inclusive and positive research cultures and environments in relevant funding calls, terms and conditions, grant reporting, and policies | Institutions planning actions for specific funders' obligations can insert these obligations into the relevant section of the institution template.
* The Researcher Development Concordat defines researchers as individuals whose primary responsibility is to conduct research and who are employed specifically for this purpose by a higher education institution or research institute. The primary audience is research staff, e.g. postdoctoral researchers, research fellows, research assistants. The Researcher Development Concordat encourages institutions to include other groups who actively engage in research as beneficiaries of their Concordat action plan. These could be postgraduate researchers; staff on teaching and research, or teaching contracts; clinicians; professional support staff; technicians.
Further hyperlinks and supplementary information (more rows can be added) |  |  |  |  | Abbreviations and glossary (more rows can be added)
1 | Use these spaces to provide links and references for information provided in the action plan. |  |  |  |  | Use these spaces to describe abbreviations and
2 | [5 empty] | terms used in the action plan.
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
N.B. This section is for reporting only, and should not be completed prior to the beginning of the action plan's term.
For brevity, the remaining obligations have been omitted from this 'Guidance' sheet.

## Tips
| HREiR Action plan template (add dates) | [6 empty] | Add institutional logo
Details
| Institution name: |  |  |  |  | The institutional audience* for this action plan includes (only include direct beneficiaries; complete or delete, as appropriate):
| Cohort number: |  |  |  |  | Audience (direct beneficiaries of the action plan) |  | Number of | Comments
| Date of submission: |  |  |  |  | Research staff |  |  | Only include institutional audiences considered to directly benefit from the action plan, remembering that research staff should be prioritised.
| Institutional context: |  |  |  |  | Postgraduate researchers
Research and teaching staff
Teaching-only staff
Technicians
Clinicians
Professional support staff
Other (please provide numbers and details):
Complete for submission | [7 empty] | To be completed only when reporting on action plan
| Obligation | Action | Carried over from previous action plan? | Deadline | Responsibility | The targeted impact of the action (success measure) | Comments (optional) | Progress update | The actual impact of the action (reporting against the success measure) | Outcome (ongoing/carried forward/no further action)
Environment and Culture
Awareness and engagement
The aims of these obligations are to work towards an open and inclusive research culture, and to ensure broad understanding and awareness of this amongst researchers. Our internal evaluation revealed that researchers feel the university strategic priorities do not reflect their own (62% in a consultation said that they felt disconnected from the university's recent 'Strategy 2030'). Heads of Faculties also report from conversations at committee meetings that researchers feel the university's strategic priorities are not entirely aligned with the reality felt in specific research disciplines. Optional: Institutions can use this space (if desired) to discuss the context that frames the actions and success measures disclosed.
ECI1 | Ensure all relevant staff are aware of the Concordat
ECI2 | Ensure institutional policies and practices relevant to researchers are inclusive, equitable and transparent, and are well-communicated to researchers and their managers. | Providing actions for every obligation is not mandatory, although action plans should aim to target those in their priority areas and/or those highlighted by researchers during the internal evaluation.
ECI6 | Regularly review and report on the quality of the research environment and culture, including seeking feedback from researchers, and using the outcomes to improve institutional practices. | Host programme of Faculty- and institution-wide workshops on research culture, capturing local and broader views on key themes in research and reflecting these with the institution's 'Strategy 2030' priorities. Gather a comprehensive range of anonymous views from research staff on how they feel their Faculty research environment compares to the institution as a whole through quarterly Faculty pulse surveys. | no yes | Jul-23 Being specific (rather than only stating "ongoing" or "annually") indicates that reporting has been properly scheduled and that actions are timebound. May-23 | • RCWG • Heads of Faculties • PVC-RI • Faculty-HR • RCWG Broad and specific responsibility can show a joined-up approach to working, connects institutional stakeholders around the Researcher Development Concordat and also shares the workload. | • Host quarterly workshops for each Faculty, and biannual institutional workshops. Success measures like this (i.e., "action completed") are acceptable but should be complemented by other measures that show the impact of the action. • Drafting of workshop reports led by research staff attendees, and reports instated as a standing agenda item at Faculty committee meetings. • At least 30 research staff attendance (on average) at Faculty workshops. Positive post-event feedback from at least 80% of research staff attendees. • At least 40% of research staff (on average) across all 5 Faculties respond to Faculty pulse surveys. Success measures like these allow institutions to qualitatively and quantitatively assess progress against the obligation. Note the words underlined in the obligation and consider how the success measures could align with these. Setting numerical (i.e., SMART) targets can provide an unambiguous benchmark to report progress against in the future. |  | Programme of workshops conducted digitally due to ongoing COVID restrictions (1). Attendance was encouraging, with a good number of research staff joining and contributing to both discussions and the chat function. Research staff were less engaged in the reporting of the workshops than hoped, partially attributed to the less stimulating setting of online events. Feedback from research staff attendees was very positive, and both this feedback and the workshop discussion points were fed into Faculty committee meetings. In one instance, this prompted a Head of Faculty to set up focus groups to explore one particular issue more closely. Faculty pulse survey engagement was encouraging, albeit variable across the Faculties. The findings and trends will help inform future Concordat action plans and the university's Research Culture manifesto. By describing the action's progress in narrative form, institutions can explain success in greater detail, or mitigate challenges experienced, by providing helpful contextual information. | • All 5 Faculties' workshops held quarterly, as well as two workshops held at an institutional level. • Workshop reporting only partially led by research staff across the Faculties. All Faculty committees successfully instated research culture reports as an agenda item. • 34 research staff attended each workshop on average. 86% of research staff attendees gave positive post-event feedback, with 84% saying they "found the workshop to be helpful". • 38±3% of research staff responded to pulse surveys across all Faculties, although some only received 35% research staff response rates. Ensuring you report against all success measures provides a better assessment of the impact achieved and shows commitment to researchers that the institution cares about their views and behaviour. | no further action (action now considered normal business) After selecting from one of the set responses in the column header, institutions can briefly indicate the rationale for this decision (e.g., "action successfully embedded" or "action delayed, partially completed").
ECR1 | Encourage researchers to actively contribute to the development and maintenance of a supportive, fair and inclusive research culture and be a supportive colleague, particularly to newer researchers and students. | Even if no action is intended/needed, it is encouraged to include success measures that show how different stakeholders engage with/benefit from other actions. |  | Jul-23 | • RCWG | At least 70% of research staff answering CEDARS q42.4 ("feel included in your immediate research environment/group") agree or strongly agree (CEDARS 2021: 62%) | Survey response rate in 2021: 16% research staff (n=147) Optional: This space can be used to provide details not suitable for the other columns. For example, you can add information relevant to an action and/or a success measure to help demonstrate feasibility. | CEDARS response rate improved considerably after a campaign of targeted communications. This coincided with less positive responses for q42.4 than anticipated, suggesting that the university is now successfully reaching a previously 'silent' yet dissatisfied group of research staff with the survey. | 64% of research staff responded agree/strongly agree for CEDARS q42.4. 22% of all research staff (n=202) responded to CEDARS.
* The Researcher Development Concordat defines researchers as individuals whose primary responsibility is to conduct research and who are employed specifically for this purpose by a higher education institution or research institute. The primary audience is research staff, e.g. postdoctoral researchers, research fellows, research assistants. The Researcher Development Concordat encourages institutions to include other groups who actively engage in research as beneficiaries of their Concordat action plan. These could be postgraduate researchers; staff on teaching and research, or teaching contracts; clinicians; professional support staff; technicians.
Further hyperlinks and Supplementary Information (more rows can be added) |  |  |  |  | Abbreviations and Glossary (more rows can be added)
1 | www.university.ac.uk/researchculture/researchcultureworkshops/summary |  |  |  | PVC-RI | Pro-Vice Chancellor for Research & Innovation
2 | Using these spaces can help keep the main body of the action plan as concise as possible. |  |  |  | RCWG | Research Culture Working Group
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
This sheet gives a hypothetical response to a group of obligations under Environment and Culture > Awareness and engagement.
Tips and advice are shown alongside to highlight how to organise actions and success measures to deliver the most impact, as well as to demonstrate a transparent and compelling approach to reporting on progress and the original success measure.
For brevity, the remaining obligations have been omitted from this 'Tips' sheet.